## Full calendar
2016 SHUSA RAS Exercise Timeline
| Monday | Tuesday | Wednesday | Thursday | Friday
| 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05
February
| 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12
|  |  | Capital/CCAR: ALCO PPT, Excel w/ metrics, Capital expectations | New Group RAS presentation documented
| 2016-02-15 | 2016-02-16 | 2016-02-17 | 2016-02-18 | 2016-02-19
| Socialize new Group RAS presentation with relevant contributors |  |  |  | ORM: Reconvene w/ B. McVane on Group metric availability
Prepare summary Glossary to append to RAS Board Document and circulate
Mkt. Risk: Confirm which metrics applicable at SHUSA and at each entity; defs. to be used for local RAS and if differ from Group defs.
| 2016-02-22 | 2016-02-23 | 2016-02-24 | 2016-02-25 | 2016-02-26
|  |  |  | CR: Credit metrics check point SBNA Final list of Credit Metrics | IHC: All qualitative statements agreed, first draft of RAS received all entities
| 2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04
March |  | Capital/CCAR: IHC Entities CCAR Run | Loss in Stress prep
Group RAS presentation prep
Entity metric list closed
| 2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11
| Loss in Stress prep |  |  |  | Loss in Stress first run
Group RAS presentation prep
Update US Glossary with new metrics and update Board summary
| 2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18
Group RAS presentation prep
CR: Credit metrics (non-CCAR) due in final form
final form
| 2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25
OW engagement - prep work
Group RAS presentation prep
| Capital/CCAR: Deliver credible 1st pass of CCAR results to SHUSA RA |  |  |  | Loss in Stress second run
| 2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01
OW engagement - prep work
Group RAS presentation prep
US RAS Board presentations - First draft from Entities
Group RAS Team checkpoint
| 2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08
April | OW engagement - prep work |  | OW engagement - loss allocation and metric calibration
Group RAS presentation prep
Capital/CCAR: SHUSA Cons. CCAR Run
| 2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15
OW engagement - loss allocation and metric calibration
Group RAS presentation prep
US RAS Board presentations - Second draft from Entities
|  |  |  | SC RA: Submit materials for ERMC | Mkt. Risk: Deliver agreed levels for each metric
| 2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22
OW engagement - loss allocation and metric calibration
| First draft full Group RAS presentation |  |  |  | Group RAS Team checkpoint
SC ERMC Meeting
| 2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28 | 2016-04-29
OW engagement - loss allocation, metric calibration, US RAS presentations
Group RAS presentation prep
US RAS Board presentations - Third draft from Entities
| 2016-05-02 | 2016-05-03 | 2016-05-04 | 2016-05-05 | 2016-05-06
May | OW engagement - loss allocation, metric calibration, US RAS presentations
Group RAS presentation prep
First draft full US RAS presentations from the Entities
|  |  |  | SHUSA RA: Submit materials for ERMC meeting | Mkt. Risk: Agreed levels for each metric by entity with Group
Group RAS Team checkpoint
| 2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-13
OW engagement - loss allocation, metric calibration, US RAS presentations
Group RAS presentation prep
SHUSA RAS presentation first draft
US RAS - Socialization with the business - all entities
| 2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20
OW engagement - loss allocation, metric calibration, US RAS presentations
Group RAS presentation prep
SHUSA RAS presentation second draft
US RAS - Socialization with the business - all entities
|  | SHUSA: S. Powell and B. Gunn to review SHUSA Group RAS for ERC |  | SHUSA RA: Review with Group (P. Corral) | Group RAS Team checkpoint
SBNA RA: Submit materials for ERMC
| 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27
OW engagement - loss allocation, metric calibration, US RAS presentations
SHUSA RAS presentation third draft
US RAS - Socialization with the business - all entities
| SHUSA, SBNA"Short" Board Meeting |  | SBNA ERMC Meeting | SHUSA RA: Present SHUSA Group RAS to ERC (fmr. CDR) for review
| 2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03
June | OW engagement - loss allocation, metric calibration, US RAS presentations
SHUSA RAS presentation final draft
US RAS - Socialization with the business - all entities
SHUSA RAS - Review with Scott, Brian, senior leadership
| 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10
BSI RA: Submit RAS to Legal for inclusion in BoD meeting
SHUSA RA: Submit RAS for ERMC
SBNA RA: Submit RAS for ERMC
| 2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17
|  |  | SHUSA ERMC Meeting | BSI (Miami) Risk Cmte. Meeting | SIS (NY) RA: Submit RAS to Legal for inclusion in BoD meeting
|  |  | SBNA ERMC Meeting | BSPR (PR) RA: Submit RAS to Legal for inclusion in BoD meeting
| 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24
|  | SHUSA RA: Submit RAS to Legal for inclusion in BoD meeting |  | BSPR (PR) Board Risk Cmte. Meeting | BSPR (PR) Board Meeting
SIS (NY) Board Meeting
| 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01
July |  | SHUSA Board Risk Cmte. Meeting | SHUSA Board of Directors Meeting
|  | SHUSA Cons. RAS to be presented for approval | SHUSA Cons. RAS to be presented for approval
|  | SBNA Board Risk Cmte. Meeting | SBNA Board Meeting
| 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08
SC Risk Cmte. Meeting
| 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15
SC RA: Submit materials for ERMC
| 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22
SC ERMC Meeting
| 2016-07-25 | 2016-07-26 | 2016-07-27 | 2016-07-28 | 2016-07-29
|  |  | SC Board Risk Cmte. Meeting | SC Board Meeting
Legend:
Inbound requested information
Oliver Wyman engagement
Group review
SHUSA RAS Team deliverable
ERMC/Lv 1 Risk Cmte Meeting
U.S. IHC entity board meeting
SHUSA board meeting

## Mar
2016 SHUSA RAS Exercise Timeline
March
Monday | Tuesday | Wednesday | Thursday | Friday
2016-02-29 | 2016-03-01 | 2016-03-02 | 2016-03-03 | 2016-03-04
Capital/CCAR: IHC Entities CCAR Run
2016-03-07 | 2016-03-08 | 2016-03-09 | 2016-03-10 | 2016-03-11
2016-03-14 | 2016-03-15 | 2016-03-16 | 2016-03-17 | 2016-03-18
CR: Credit metrics (non-CCAR) due in
final form
2016-03-21 | 2016-03-22 | 2016-03-23 | 2016-03-24 | 2016-03-25
2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01
Legend:
Inbound requested information
Group review
U.S. IHC entity board meeting
SHUSA board meeting

## Apr
2016 SHUSA RAS Exercise Timeline
April
Monday | Tuesday | Wednesday | Thursday | Friday
2016-03-28 | 2016-03-29 | 2016-03-30 | 2016-03-31 | 2016-04-01
2016-04-04 | 2016-04-05 | 2016-04-06 | 2016-04-07 | 2016-04-08
| Capital/CCAR: SHUSA Cons. CCAR Run |  | BSI (Miami) Board Meeting
2016-04-11 | 2016-04-12 | 2016-04-13 | 2016-04-14 | 2016-04-15
Mkt. Risk: Deliver agreed levels for
each metric
2016-04-18 | 2016-04-19 | 2016-04-20 | 2016-04-21 | 2016-04-22
|  | BSPR (PR) Board Meeting |  | SIS (NY) Board Meeting
2016-04-25 | 2016-04-26 | 2016-04-27 | 2016-04-28 | 2016-04-29
| SBNA Board Meeting |  | SC Board Meeting
Legend:
Inbound requested information
Group review
U.S. IHC entity board meeting
SHUSA board meeting

## May
2016 SHUSA RAS Exercise Timeline
May
Monday | Tuesday | Wednesday | Thursday | Friday
2016-05-02 | 2016-05-03 | 2016-05-04 | 2016-05-05 | 2016-05-06
Mkt. Risk: Agreed levels for each
metric by entity with Group
2016-05-09 | 2016-05-10 | 2016-05-11 | 2016-05-12 | 2016-05-13
2016-05-16 | 2016-05-17 | 2016-05-18 | 2016-05-19 | 2016-05-20
SHUSA RA: Review with Group
(P. Corral)
2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27
SHUSA "Short" Board Meeting |  |  | SHUSA RA: Present SHUSA Group
RAS to ERC (fmr. CDR) for review
2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03
Legend:
Inbound requested information
Group review
U.S. IHC entity board meeting
SHUSA board meeting

## Jun
2016 SHUSA RAS Exercise Timeline
June
Monday | Tuesday | Wednesday | Thursday | Friday
2016-05-30 | 2016-05-31 | 2016-06-01 | 2016-06-02 | 2016-06-03
2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10
2016-06-13 | 2016-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17
2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24
2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01
SHUSA Board of Directors Meeting
SHUSA Cons. RAS to be presented for
approval
Legend:
Inbound requested information
Group review
U.S. IHC entity board meeting
SHUSA board meeting