## Slide 1
SHUSA COMMITTEE/BOARD
Draft v.1
For Review
Author: Beatriz Shapiro, Director, Risk appetite SHUSA
SHUSA Risk Appetite Statement– January Report
February 2016

## Slide 2
Key Milestones
ECB review of the SHUSA RAS: the meetings and supporting documentary submissions covered the US RAS documentation, methodology, approved metrics, alignment to Santander Group RAS, and Group validation of the SHUSA RAS.
All Risk Appetite documentation is in place across SHUSA, SC and SBNA:
  Risk Appetite Framework
  Risk Appetite Statement (RAS) Monitoring and Escalation Procedure
  RAS Monthly reporting and related procedures
  RAS Metrics Database
  Glossary of Metrics
  SBNA: Update provided to OCC on new Risk Appetite program and plans for 2016
Internal Audit concluded in December with two recommendations:
  Finalize Risk Appetite metric glossary – due 2.29.16 – closed 2.5.16
  Plan for metric testing and execution throughout the year – due 9.15.16
New metrics and updates to existing metrics – see slide 3
Next Steps - Q1 and Q2 2016
Annual review of the SHUSA RAS – started November 2015 - due June 2016.
  Aligned to 2016 CCAR
  Extended to all IHC entities: SBNA, SC, BSI Miami, Banco Santander Puerto Rico, Santander Securities LLC, SIS New York
  Will include where applicable new metrics approved by Group Board in December 2015
Working with Risk MI to include RAS metrics into RDA project plan
Q4’15 – Summary review (1/2)

## Slide 3
The Boards of SC and SBNA approved updates and new metrics throughout Q4’15
UPDATES
SC Auto Net Charge-off Limit (Approved Oct-15) The Auto NCO rate levels were lower than the net charge-off rate forecast in SC’s Strategic Plan (P-18). A review of the original RAS calibration exercise concluded that, since there would be no dividend payment under a stress scenario, ~10 bps of additional loss rate budget could be allocated to Auto NCOs. The metric levels were increased from 7.8% to 7.9% (amber trigger) and from 8.5% to 8.6% (red limit).
SC Common Equity Tier 1 (CET1) (Approved Dec-15) Increase in the trigger from 10% to 11% and limit from 8.75% to 9.45% after the annual recalibration exercise of capital expectations.
NEW METRICS
SC Total Risk Weighted Assets (RWAs) (Approved Oct-15)
Risk Weighted Asset (RWA) limit based on a CET1 ratio of 11%. The limit is calculated using prior month CET1 capital. The trigger is set $2BN below the limit.
  SBNA Consumer Financial Protection Bureau (CFPB) Complaints (Approved Dec-15) The CFPB provides consumers the ability to share their complaints with financial companies. The trigger was set to be the monthly peer group average of 36 complaints. The limit was set to be the 3rd quartile figure of the peer group distribution of 41 complaints.
SBNA # of OCC enforcement actions (Approved Dec-15) Since the OCC does not issue MRIAs, SBNA is using OCC enforcement actions. As with the MRIA metric at SHUSA, the OCC enforcement actions metric is set to a zero appetite level.
Q4’15 – Summary review (2/2)

## Slide 4
2. Risk Appetite Statement Dashboard
Focus of concern
Area of attention
Not a concern
Overall Status
1.Capital adequacy
2.Credit risk
4.Liquidity / Funding risk
5. Interest rate risk
7.Strategic risk
8.Operational risk
10.Compliance and Reputational risk
9.Model risk
3. Residual value risk
6. MTM Portfolio risk
  Two breaches in concentration metrics. 1 NCO Breach.
    Industry Exposure: In breach for the Finance & Insurance industry group. Solvency is working to determine an action plan, which may include exposure reduction to specific customers, a segment division to separate financial companies from companies engaged in leasing activities, or a limit increase.
    The # of counterparties with SRR < 5.0 and exposure > $100MM remained in breach at 5. Three GCB counterparties (Vale, Freeport-McMoRan, and Teekay Offshore) were downgraded to below a 5 SRR.
    Net Charge-Off GCB remains in breach
Metrics within appetite.
Key Breach Actions
Metrics within appetite
  SBNA Gross losses / gross margin From 1.5% in Q3 2015 to 3.85% in Q4 2015. increase primarily due to $22.6 MM of losses in December, including a $13.5 MM Overdraft Opt-in Provision
  SHUSA Backlog of Tier 1 models not appropriately approved Remains in breach
Industry Exposure: Action plan in development; data scrub underway to complete due diligence
SRR<5 concentration:
Action plan submitted by Solvency – Credit team met with OCC to seek relief from risk rating directive for strongest sponsors; changes will be considered by OCC
RAS Metric Summary
Qualitative assessment
  -The industry exposure breach is not a major concern as the majority of counterparties in the Finance and Insurance group are not true Financial Institutions, but rather leasing and mortgage warehouse companies.
  Large exposures in oil and gas and commodity sectors under stress due to sector deterioration
  -The CRE counterparty breach is primarily the result of an OCC directive to risk rate CRE Construction transactions as low pass, causing otherwise strong One Obligor relationships to not reach the 5.0 risk rating hurdle.
  -A $24MM charge-off of Oil&Gas account Paragon Offshore Limited. SBNA’s participation in a syndicated loan was sold on Nov. 24th at a discount of 68.7%.
  CRE concentration, due to increase with GCB loan sale, facing increasing regulatory scrutiny due to credit risk and underwriting standards.
  Due to an increased model inventory and regulatory feedback on the model validation calendar, targeted for February inclusion in RAS.
4 OCC enforcement actions against SBNA:
1) Mortgage Foreclosure Consent Order 2) Commitment to Address Findings from Pre-charter Conversion 3) BSA/AML Part 30 Notice 4) Sovereign Identity Protector Consent Order
  Pending SC
  Pending SC
Metrics within appetite
Pending SC
SHUSA decrease to 25 open MRIA- 3 closed
The # of OCC Enforcement Actions remain in breach
Overall Status
2.Credit risk
Key Breach Actions
RAS Metric Summary
Qualitative assessment

## Slide 5
Risk Appetite Statement
Amber and Red Metrics |  |  |  |  |  |  | 
Entity / portfolio | Risk Type | Metrics | Jan 16 | Dec 15 | Nov 15 | Amber limit | Red limit
SHUSA | Liquidity / funding risk | Survival Horizon under stress1 | TBD | 82 days | 82 days | 90 days | 60 days
 | Model risk | Backlog of Tier 1 models not appropriately approved | Total 136 SHUSA – 2 SC – 24 SBNA – 43 Other ent. – 67 | Total 145 SHUSA – 1 SC – 23 SBNA – 48 Other ent. – 73 | Total 146 SHUSA – 1 SC – 23 SBNA – 52 Other ent. – 70 | N/A | 4Q2015 – 102 2Q2016 – 90 4Q2016 – 60 2Q2017 – 30 4Q2017 – 0
 | Compliance and reputational risk | # Matters Requiring Immediate Attention (MRIAs) | 25 | 28 | 28 | N/A | 0
SBNA | Credit | Net charge-off rate GCB | 0.26% | 0.28% | 0.00% | 0.2% | 0.4%
 |  | # of counterparties with Santander Risk Rating (internal) < 5.0 and exposure > $100MM2 | 5 | 5 | 2 | N/A | 0
 |  | Industry exposure (by OCC group) | $5.0B (Financial & Insurance) | $5.1B (Financial & Insurance) | $6.0B (Financial & Insurance) | $4.5B | $5.0B
 | Operational Risk | Gross losses / gross margin | 3.85% | 3.85% | 1.50% | 3.0% | 5.0%
 | Compliance and reputational risk | # of OCC enforcement actions | 4 | 4 | 4 | N/A | 0
SC | Credit | Net charge-off rate SC Unsecured |  | 18.79% | 18.50%3 | 18.0% | 20.0%
 |  | 61+ Auto SC |  | 4.80% | 4.61% | 4.40% | 4.90%
 | Liquidity / funding risk | Available SC committed liquidity / average projected net originations2 | 5.7 months | 7.5 months | 8.2 months | < 6 months | < 5 months
 | Strategic risk | SC Total Risk Weighted Assets (RWAs) |  | $37.7B(with PL) $35.3B (excl.PL) | $36.6B(with PL) $34.3B (excl.PL) | $36.7B | $38.7B
  Metric is on a one month lag
  A Santander Risk Rating (internal rating scale) of 5.0 maps to a BB+ according to the S&P rating scale
  RECAST: Unsecured Credit metrics for Nov’15 were recast after data cleanse. Previously reported values: Nov’15 18.52%.

## Slide 6
Monthly Metrics |  |  |  |  |  |  |  |  |  |  | 
Risk type | Entity | Metrics |  |  |  | BHC Baseline scenario |  |  | BHC Stress scenario |  | 
 |  |  | Jan 16 | Dec 15 | Nov 15 | BHC Base | Amber trigger | Red limit | BHC Stress | Amber trigger | Red limit
Capital adequacy1 | SHUSA | * Common Equity Tier 1 Ratio | 11.38% | 11.77% | 12.05% | 11.40% | 11.00% | 10.50% | 9.4% | 7.50% | 6.50%
 |  | Tier 1 Risk-based Capital Ratio | 12.75% | 13.23% | 13.39% | 12.40% | 12.50% | 12.00% | 9.5% | 9.00% | 8.00%
 |  | Total Capital Ratio | 14.58% | 15.01% | 15.25% | 14.70% | 14.50% | 14.00% | 11.8% | 11.00% | 10.00%
 |  | * Tier 1 Leverage Ratio | 11.31% | 11.68% | 11.74% | 11.90% | 10.25% | 9.75% | 9.0% | 7.00% | 5.00%
 |  | Tangible Common Equity Ratio |  |  | 10.95% | 11.40% | 10.50% | 10.00% | 10.5% | 7.25% | 6.25%
 | SBNA | * Common Equity Tier 1 Ratio | 13.67% | 13.81%2 | 13.72% | 12.70% | 11.00% | 10.75% | 10.2% | 7.55% | 6.50%
 |  | Tier 1 Risk-based Capital Ratio | 13.67% | 13.81%2 | 13.72% | 12.70% | 12.50% | 12.25% | 10.2% | 9.05% | 8.00%
 |  | Total Capital Ratio | 15.00% | 15.09% | 15.00% | 14.50% | 14.30% | 14.05% | 12.5% | 11.05% | 10.00%
 |  | * Tier 1 Leverage Ratio | 11.36% | 11.46% | 11.49% | 11.70% | 9.95% | 9.70% | 9.7% | 7.05% | 5.00%
 |  | Tangible Common Equity Ratio | 11.15% | 11.10% | 11.17% | 11.90% | 9.90% | 9.65% | 11.7% | 7.00% | 6.00%
 | SC | * Common Equity Tier 1 Ratio | 11.05% | 11.18% | 11.64% | 11.60% | 11.00%3 | 9.45% | 5.7% | 6.25% | 5.25%
 |  | Tier 1 Risk-based Capital Ratio | 11.05% | 11.18% | 11.64% | 11.60% | 10.00% | 8.75% | 5.7% | 6.25% | 5.25%
 |  | Tangible Common Equity Ratio | 11.61% | 11.84% | 12.32% | 12.20% | 10.50% | 9.25% | 6.0% | 6.75% | 5.75%
  Transitional as the regulatory requirements are a core RAS objective and will follow the glide-path
  Recast SBNA value change from 18.30% to 18.31%
  SC is currently managing to a CET1 ratio of 11%
Risk Appetite Statement
  * Mandated by Santander Group

## Slide 7
Monthly Metrics |  |  |  |  |  |  | 
Risk type | Metrics | Entity / portfolio | Jan 16 | Dec 15 | Nov 15 | Amber limit | Red limit
Credit | Net charge-off rate1 | SC Auto** |  | 7.12% | 6.98%2 | 7.8%2 | 8.5%2
 |  | SC Unsecured** |  | 18.79% | 18.50%2 | 18.0% | 20.0%
 |  | SBNA Retail | 0.69% | 0.71% | 0.78% | 1.0% | 1.3%
 |  | SBNA Small Business + Business Banking + Auto | 0.56% | 0.55% | 0.62% | 0.7% | 0.9%
 |  | SBNA C&I | 0.30% | 0.34% | 0.28% | 0.5% | 0.7%
 |  | SBNA CRE | 0.06% | 0.04% | 0.06% | 0.3% | 0.5%
 |  | SBNA GCB | 0.26% | 0.28% | 0.00% | 0.2% | 0.4%
 | % 61+ days past due | SC Auto** |  | 4.80% | 4.61%2 | 4.4% | 4.9%
 |  | SC Unsecured** |  | 6.64% | 7.02%2 | 7.0% | 8.0%
 | % 60+ days past due | SBNA Retail | 2.25% | 2.17% | 2.25% | 5.0% | 7.5%
 | * # of counterparties with Santander Risk Rating (internal) < 5.0 and exposure > $100MM 3 | SHUSA / SBNA | 5 | 54 | 2 | N/A | 0
 | * Industry exposure (by OCC group) | SHUSA / SBNA | $5.0B (Financial & Insurance) | $5.1B (Financial & Insurance) | $6.0B (Financial & Insurance) | $4.5B | $5.0B
 | * CRE exposure (excl. Multifamily) | SHUSA / SBNA | $8.8B | $8.6B | $8.7B | $10.0B | $10.5B
 | * Multifamily exposure | SHUSA / SBNA | $10.3B | $10.4B | $10.3B | $10.5B | $11.0B
 | * Single obligor exposure | SHUSA / SBNA | $500MM | $500MM | $500MM | N/A | $500MM
 | * Top 20 obligors exposure | SHUSA / SBNA | $6.45B | $6.56B | $6.48B | $7.0B | $8.0B
Net charge-off metric has been revised to a 12-month rolling calculation
Unsecured Credit metrics for Nov’15 were recast after data cleanse. Previously reported values: Nov’15 18.52%
A Santander Risk Rating (internal rating scale) of 5.0 maps to a BB+ according to the S&P rating scale
CCMIS data extract - value changed from 2 to 5 cases in December
  * Mandated by Santander Group
Risk Appetite Statement
  ** Pending SC numbers

## Slide 8
Monthly Metrics |  |  |  |  |  |  | 
Risk type | Metrics | Entity / portfolio | Jan 16 | Dec 15 | Nov 15 | Amber trigger | Red limit
Residual value risk | Net residual value exposure** | SHUSA / SC |  | 1.55% | 1.51% | 5.0% | 9.0%
Liquidity / funding risk | * Survival Horizon under stress1 | SHUSA | TBD | 82 days | 82 days | 90 days | 60 days
 |  | SBNA | TBD | 150 days | 180 days | 90 days | 60 days
 | * Liquidity Coverage Ratio | SHUSA | 229.3% | 252.7% | 256.2% | 140% | 125%
 |  | SBNA | 183.0% | 193.8% | 189.5% | 120% | 110%
 | * Structural Funding Ratio | SHUSA | 109.1% | 109.6% | 109.1% | 105% | 100%
 |  | SC | 87.3% | 87.1% | 89.4% | 75% | 70%
 |  | SBNA | 122,7% | 123.5% | 121.0% | 105% | 100%
 | Available SC committed liquidity / average projected net originations | SHUSA / SC | 5.7 months | 7.5 months | 8.2 months | < 6 months | < 5 months
Interest rate risk | Net interest income sensitivity (+/- 100bps shock) | SHUSA | $(92)MM | $(78)MM | $(96)MM | $(120)MM | $(140)MM
 |  | SC | $(51)MM | $(47)MM | $(39)MM | $(75)MM | $(100)MM
 |  | SBNA | $(84)MM | $(82)MM | $(87)MM | $(150)MM | $(200)MM
 | Market value of equity sensitivity (+/- 200 bps shock) | SHUSA | $(830)MM | $(614)MM | $(667)MM | $(1,070)MM | $(1,220)MM
 |  | SC | $(208)MM | $(227)MM | $(210)MM | $(240)MM | $(300)MM
 |  | SBNA | $(776)MM | $(552)MM | $(621)MM | $(825)MM | $(1,100)MM
Mark-to-market portfolio risk | Mark-to-market Value at Risk (VaR) | SHUSA | $8.3MM | $8.5MM | $9.5MM | $24.4MM | $28MM
  1. Metric is on a one month lag
  * Mandated by Santander Group
Risk Appetite Statement
  ** Pending SC numbers

## Slide 9
Monthly/Quarterly Metrics |  |  |  |  |  |  | 
Risk type | Metrics | Entity / portfolio | Jan 16 | Dec 15 | Nov 15 | Amber trigger | Red limit
Strategic risk | SC subprime assets as % of SHUSA credit exposure1 ** | SHUSA / SC |  | 19.6% (with PL) 18.0% (excl. PL) | 19.6% (with PL) 18.0% (excl. PL) | 23% | 25%
 | SC Total Risk Weighted Assets (RWAs) 2 ** | SHUSA / SC |  | $37.7B(with PL) $35.3B (excl.PL) | $36.6B(with PL) $34.3B (excl.PL) | $38.5B | $40.5B
Model risk | Backlog of Tier 1 models not appropriately approved | SHUSA | Total 136 SHUSA – 2 SC – 24 SBNA – 43 Other ent. – 67 | Total 145 SHUSA – 1 SC – 23 SBNA – 48 Other ent. – 73 | Total 146 SHUSA – 1 SC – 23 SBNA – 52 Other ent. – 70 | N/A | 4Q2015 – 102 2Q2016 – 90 4Q2016 – 60 2Q2017 – 30 4Q2017 – 0
Compliance and reputational risk | # Matters Requiring Immediate Attention (MRIAs) | SHUSA | 25 | 28 | 28 | N/A | 0
 | Serviced for others monthly net charge-off rate3 ** | SHUSA / SC |  | 0.80% | 0.78% | 1.5% | 2%
 | CFPB Complaints | SBNA | 22 | 25 | 32 | 36 | 41
 | # of OCC enforcement actions | SBNA | 4 | 4 | 4 | N/A | 0
 |  |  | 4Q 15 | 3Q 15 | 2Q 15 | Amber trigger | Red limit
Operational risk | Gross losses / gross margin | SHUSA | 1.60% | 1.00% | 0.47% | 3.0% | 5.0%
 |  | SC | 0.57%4 | 0.80% | 0.07% | 3.0% | 5.0%
 |  | SBNA | 3.85% | 1.50% | 1.46% | 3.0% | 5.0%
 | Frequency of events >$200K in losses | SHUSA | 3 | 7 | 1 | 9 | 16
 |  | SC | 1 | 4 | 1 | 3 | 6
 |  | SBNA | 2 | 3 | 0 | 6 | 10
  Subprime is defined as FICO < 630 or no FICO score available
  Limit is recalculated every month as prior month's CET1 divided by 11%, amber trigger is $2BN less
  For those portfolios exposing SC to reputational risk
  Methodology changed to better align with SHUSA CCAR process, and Madrid reporting. The change is the timing of events being report from closed date to open date, the result is a one time true‐up of $21.95mm on 12/31. (With the true‐up included, the 4th quarter value would within Risk Appetite at approximately 1.78%)
Risk Appetite Statement
  ** Pending SC numbers

## Slide 10
Risk type | Metrics | Entity / portfolio | ∆ BHC Stress and baseline |  |  |  | Amber trigger | Red limit
Residual value risk | Residual value deterioriation1 | SHUSA / SC |  |  | $475MM |  | $500MM | $525MM
Risk type | Metrics | Entity / portfolio |  |  | BHC Stress |  | Amber trigger | Red limit
Credit risk | CCAR loss budget2 | SC Auto |  |  | $6,375MM |  | $6,575MM | $7,000MM
 |  | SC Unsecured |  |  | $1,150MM |  | $1,175MM | $1,250MM
 |  | SBNA Retail |  |  | $650MM |  | $675MM | $725MM
 |  | SBNA Wholesale |  |  | $1,225MM |  | $1,250MM | $1,350MM
 |  | SBNA GBM |  |  | $350MM |  | $375MM | $400MM
Strategic risk | Pre-provisioned net revenue (PPNR) impairment | SHUSA |  |  | $3,700MM |  | $3,825MM | $4,100MM
 |  | SC |  |  | $2,500MM |  | $2,575MM | $2,775MM
 |  | SBNA |  |  | $1,200MM |  | $1,250MM | $1,350MM
 | * Loss in stress 3 | SHUSA |  |  | 139% |  | 100% | 150%
Projected 9Q cumulative increase in Leased Vehicle Expense between BHC Stress and Baseline scenarios – assumes all attributed to SC
  Projected 9Q cumulative losses by portfolio under the BHC Stress scenario
  Projected losses in stress scenario aligning to Group (CCAR FRB Adverse scenario is used as it is the scenario that is the closest to the ICAAP scenario run by Group)
Risk Appetite Statement
  * Mandated by Santander Group
Annual Metrics